HOLY FAMILY PRIMARY AND NURSERY SCHOOL           SEN ACTION PLAN                YEAR: 2021-22

| PRIORITY: To fully implement all aspects of the SEND Act NI 2016 at the school level by June 2022. In so doing, to ensure that all staff are upskilled in the new requirements and deliver these requirements consistently at the class level. The success of this action plan will be evidenced by 100% achievement of the established success criteria. | BASELINE: With the advent of the SEND Act NI 2016 and the required implementation of the Act in school this academic year, an opportunity exists to provide a whole school focus on this process. This action plan will provide such a focus. |
| --- | --- |
| TARGET/S (Aspects to be addressed) | SUCCESS CRITERIA (How we will know we’ve succeeded) | TASKS (Action to be taken) | TIMESCALE (When/how long will it take?) | STAFF INVOLVEMENT | RESOURCES (Human/material/ include support required) |
| 1. Appoint a new SENCO/LSC for N- P3 2. Appoint a new SENCO/LSC for P4- P7 3. Ensure that the new SENCOs/LSCs are fully trained on the requirements of the role 4. Ensure that the new SENCOs/LSCs are fully trained on the requirements of the SEND Act NI 2016 are completed 5. Create and communicate a whole school SEN provision map for each year group related to each area of need is completed 6. Create a new SEN Code of Practice register aligned to the Code of Practice stages 7. Create the required Individual Education Plans for each pupil on the new Code of Practice in line with the school’s SEN policy 8. Implement the required Personal Learning Plans for each pupil on the new Code of Practice once they become available 9. Review and refine all SEN processes and procedures to ensure that there is enhanced efficiency in our holistic SEN provision 10. Deliver a minimum of four whole staff Inset sessions related to the SEND ACT and its implications for practice 11. Create a Holy Family specific SEN effective strategies book and circulate to all class – based staff 12. Ensure access to a minimum of two individual SEN Inset sessions for each member of the teaching by June 2022 13. Secure a holistic reduction in the percentage of our pupils on the SEN register compared to June 2021. This will be achieved by June 2022 14. Update the pupil annual report to ensure complete clarity and consistency between the annual report SEN element and the Code of Practice register | 1. The appointment of a new SENCO/LSC for N- P3 is completed 2. The appointment of a new SENCO/LSC for P4- P7 is completed 3. The upskilling of new SENCOs/LSCs on the role are completed 4. The upskilling of new SENCOs/LSCs on the requirements of the SEND Act NI 2016 are completed 5. The creation and communication a whole school SEN provision map for each year group related to each area of need is completed 6. The creation a new SEN Code of Practice register aligned to the Code of Practice stages is completed 7. The creation of the required Individual Education Plans for each pupil on the new Code of Practice in line with the school’s SEN policy are completed 8. The implementation of the required Personal Learning Plans for each pupil on the new Code of Practice, once they become available, are completed 9. All SEN processes and procedures are refined where possible so there is enhanced efficiency in our holistic SEN provision 10. Complete the delivery of four whole staff inset sessions focussed on the SEND Act and its implications for practice 11. A Holy Family specific SEN effective strategies book has been created and circulated to all class – based staff 12. Two individual SEN Inset sessions have been completed by each member of the teaching staff by June 2021 13. There is a holistic reduction in the percentage of our pupils on the SEN register compared to June 2021. This will be achieved by June 2022 14. An updated pupil annual report has been created that secures total alignment between the annual report and the Code of Practice register | 1. Develop and implement a recruitment process for a new SENCO/LSC for N- P3 2. Develop and implement a recruitment process for a new SENCO/LSC for P4 – P7 3. Develop and implement a training programme for the new SENCOs/LSCs to include training by principal, SENCO, ex SENCO and EA staff 4. Develop and implement a training programme for the new SENCOs/LSCs on the new SEND Act 5. Review of all SEN provision within the school including those delivered by external agencies and categorise the provision for each type of special need identified 6. Review all the pupils on the updated Code of Practice and compare against the June 2021 register to ensure correct alignment 7 & 8. Maintain the delivery of our Individual Education Plan (IEP) process until it is superseded by an agreed Personal Learning Plan (PLP) system. The IEP and PLP processes will involve the creation of termly plans. 9. Conduct a holistic overview of all our SEN processes so as to identify and eradicate inefficiencies. Following review, implement adjustments so that efficiencies are maximised 10. Create and deliver a minimum of four whole staff training sessions that will enable all staff to deliver the full requirements of the SEND Act 11. Review DE SEN strategies booklet/ EA good guidelines booklet and audit staff on effective strategies across the SEN spectrum. This will be done prior to booklet creation 12. Identify and deliver access to a range of SEN courses that each teacher will avail of two 13. Via focusing SEN provision on delivering outcomes, reduce the percentage of pupils on the SEN Code of Practice register. This will be delivered by June 2021 14. Review the requirements of the Code of Practice and the various provision formats within school. Ensure that the provision format is noted on revised annual report that mirrors the Code of Practice stages | 1 & 2 – September 2021 3 – November 2021 4 – March 2022 5 – April 2022 6 – October 2021 7 & 8 As possible 9 – June 2022 10 – June 2022 11 June 2022 12 June 2022 13 June 2022 14 December 2021 | Board of Governors Board of Governors SENCO/LSC SENCO/LSC Whole staff/SENCO/LSC Whole staff/SENCO/LSC Whole staff/SENCO/LSC Whole staff/SENCO/LSC Teaching staff/SENCO/LSC Teaching staff/SENCO/LSC SENCO/LSC/EA Whole staff/SENCO/LSC Whole staff/SENCO/LSC | Time/Funding Time/Funding Time/Courses Time/Courses Release time Time Inset time Time Inset time Release time/Inset time Release time Time |
| MONITORING STRATEGIES (Who will lead/What form will it take?) | EVALUATION (How well did we do? - process/outcome) |
| Review of prioritised targets at the end of each half term by the SENCO/LSC and SEN Action plan team Review of SEN code of practice percentage levels at a class level each half term by the SENCO/LSC Termly report to the SLT and the BOG of target and success criteria achievement by the SENCO/LSC. Half termly evaluation feedback to each year group to be provided by the SENCO/LSC. End of action plan report to staff/SLT and BOG by the SENCO/LSC. | Half termly evaluation and formal report by SENCO/LSC on target and success achievement at a class level to staff and SLT Termly evaluation report at a class level to the B.O.G. End of action plan evaluation report by the SENCO/LSC to the staff/SLT and B.O.G. |